## Meeting log
Meeting # | Date | Meeting members | Issue discussed | Meeting results | Date for next meeting
1 | Week 1 | All members | Project kickoff. Discussed possible topics and agreed to study Software Testing as the topic. | Topic chosen: Software Testing. Roles assigned: Research, Design, Developer/Tester, Leader. | Week 2
2 | Week 2 | All members | Drafted the proposal and the project objectives. Discussed which sample app to build for demonstrating the testing techniques. | Proposal finished. Sample app chosen: Library Management System. | Week 3
3 | Week 3 | All members | Research on testing concepts: levels, methods, V-model, defect lifecycle. Built the Gantt chart. | Reading list agreed. Gantt chart added to the report. | Week 4
4 | Week 4 | All members | Listed functional and non-functional requirements for the sample app. Discussed how the requirements will drive the test cases. | Requirements list approved. Test plan outline agreed. | Week 5
5 | Week 5 | All members | Reviewed early sketches of the Data Flow Diagram and the Activity Diagram for the sample app. | DFD and Activity Diagram approved with small fixes. | Week 6
6 | Week 6 | All members | Started implementation. Agreed on the Python module breakdown (auth, members, books, loans, reports). | Five modules created on GitHub. First commits pushed. | Week 7
7 | Week 7 | All members | Coding progress review. Wrote the first unit tests. Discussed which integration tests to add. | Unit tests pass. Integration test plan agreed. | Week 8
8 | Week 8 | All members | Ran static testing (linter and peer code review) and dynamic testing with sample data. | Linter issues fixed. One defect found (empty title accepted) and patched. | Week 9
9 | Week 9 | All members | Wrote the formal test case table. Recorded the defect lifecycle for the title defect found in week 8. | Test case table finalized. Defect lifecycle documented in the report. | Week 10
10 | Week 10 | All members | Final review of the project report. Checked that all assignment requirements were covered. | Report approved. Submission folder packaged for Blackboard upload. | Submission week